## traditional 1
Task A Traditional |  |  | Task B Traditional |  |  | Task C Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
0 | 18 | 18 | 18 | 18 | 36 | 36 | 18 | 54
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D Traditional |  |  | Task E Traditional |  |  | Task AA Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
54 | 18 | 72 | 72 | 18 | 90 | 0 | 18 | 18
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD)
Task BB Traditional |  |  | Task CC Traditional |  |  | Task DD Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
18 | 18 | 36 | 36 | 18 | 54 | 54 | 18 | 72
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
18 |  | 18 | 36 |  | 36 | 54 |  | 54
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)

## traditional 2
Task A Traditional |  |  | Task B Traditional |  |  | Task C Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
0 | 18 | 18 | 18 | 18 | 36 | 36 | 18 | 54
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D Traditional |  |  | Task E Traditional |  |  | Task AA Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
54 | 18 | 72 | 72 | 18 | 90 | 0 | 18 | 18
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD)
Task BB Traditional |  |  | Task CC Traditional |  |  | Task DD Traditional
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
18 | 18 | 36 | 36 | 18 | 54 | 54 | 18 | 72
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
18 |  | 18 | 36 |  | 36 | 54 |  | 54
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)

## buffered 1
Task A Buffered |  |  | Task B Buffered |  |  | Task C Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
0 | 10 | 10 | 10 | 10 | 20 | 20 | 10 | 30
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D Buffered |  |  | Task E Buffered |  |  | Task AA Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
30 | 10 | 40 | 40 | 10 | 70 | 0 | 10 | 10
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD)
Task BB Buffered |  |  | Task CC Buffered |  |  | Task DD Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
6 | 10 | 16 | 16 | 10 | 26 | 26 | 10 | 36
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
6 |  | 6 | 16 |  | 16 | 26 |  | 26
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)

## buffered 2
Task A Buffered |  |  | Task B Buffered |  |  | Task C Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
0 | 10 | 10 | 10 | 10 | 20 | 20 | 10 | 30
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D Buffered |  |  | Task E Buffered |  |  | Task AA Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
30 | 10 | 40 | 40 | 10 | 70 | 0 | 10 | 10
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD)
Task BB Buffered |  |  | Task CC Buffered |  |  | Task DD Buffered
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
6 | 10 | 16 | 16 | 10 | 26 | 26 | 10 | 36
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
6 |  | 6 | 16 |  | 16 | 26 |  | 26
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)

## CCPM 1
Task A CCPM |  |  | Task B CCPM |  |  | Task C CCPM
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
feeding buffer
0 | 8 | 8 | 10 | 8 | 18 | 18 | 8 | 26 | 2
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D CCPM |  |  | Task E CCPM |  |  | Task AA CCPM
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
project buffer
26 | 8 | 34 | 34 | 8 | 60 | 0 | 8 | 8 | 18
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD) | [5 empty] | feeding buffer
Task BB CCPM |  |  | Task CC CCPM |  |  | Task DD CCPM |  |  | 4
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
6 | 8 | 14 | 14 | 8 | 22 | 22 | 8 | 30
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
6 |  | 6 | 14 |  | 14 | 22 |  | 22
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)

## CCPM 2
Task A CCPM |  |  | Task B CCPM |  |  | Task C CCPM
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
feeding buffer
0 | 8 | 8 | 10 | 8 | 18 | 18 | 8 | 26 | 2
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task B) |  |  | (Feed actual End time to task C) |  |  | (Feed actual End time to task D)
|  |  | (Check with actual End Time AA) |  |  | (Check with actual End Time BB)
Task D CCPM |  |  | Task E CCPM |  |  | Task AA CCPM
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
project buffer
26 | 8 | 34 | 34 | 8 | 60 | 0 | 8 | 8 | 18
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
0 |  | 0 | 0 |  | 0 | 0 |  | 0
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task E) | [5 empty] | (Feed actual End time to task B)
(Check with actual End Time CC) |  |  | (Check with actual End Time DD) | [5 empty] | feeding buffer
Task BB CCPM |  |  | Task CC CCPM |  |  | Task DD CCPM |  |  | 4
Planned |  | Planned | Planned |  | Planned | Planned |  | Planned
Begin | Est. | End | Begin | Est. | End | Begin | Est. | End
6 | 8 | 14 | 14 | 8 | 22 | 22 | 8 | 30
Actual | Numb | Actual | Actual | Numb | Actual | Actual | Numb | Actual
Begin | Rolls | End | Begin | Rolls | End | Begin | Rolls | End
6 |  | 6 | 14 |  | 14 | 22 |  | 22
(Roll extra 6 to report early) |  |  | (Roll extra 6 to report early) |  |  | (Roll extra 6 to report early)
(Feed actual End time to task C) |  |  | (Feed actual End time to task D) |  |  | (Feed actual End time to task E)